## RTM
Req ID | Module | Requirement Description | Priority | Test Case ID | Test Case Description | Test Type | Automation | Defect ID | Defect Status | Remarks
R1 | Quotes | Create new Business quote | High | TC01 | Create quote with valid details | Functional | Y | D101 | Closed | -
R1 | Quotes | Create new Business quote | High | TC02 | Create quote with missing fields | Negative | Y | D102 | Closed | Validation check
R2 | Quotes | Calculate premium based on age & plan | Critical | TC03 | Verify premium calculation logic | Functional | Y | D103 | Open | Calculation issue
R3 | Policies | Create policy from approved quote | Critical | TC04 | Generate policy from quote | Functional | Y | D104 | Closed | -
R3 | Policies | Create policy from approved quote | Critical | TC05 | Policy creation with invalid data | Negative | N | D105 | Open | Needs automation
R4 | Policies | View and update policy details | High | TC06 | Update nominee details | Functional | Y | - | - | -
R5 | Renewals | Renew policy before expiry | Critical | TC07 | Successful policy renewal | Functional | Y | D106 | Closed | -
R5 | Renewals | Renew policy before expiry | Critical | TC08 | Renewal with expired policy | Negative | Y | D107 | Closed | -
R6 | Renewals | Send renewal reminders | Medium | TC09 | Validate reminder notification | Functional | N | - | - | Manual check
R7 | Endorsements | Modify policy (address change) | High | TC10 | Update address endorsement | Functional | Y | D108 | Closed | -
R7 | Endorsements | Modify policy (address change) | High | TC11 | Invalid endorsement request | Negative | N | D109 | Open | Edge case
R8 | Endorsements | Add/remove dependents | Critical | TC12 | Add dependent to policy | Functional | Y | D110 | Closed | -
R8 | Endorsements | Add/remove dependents | Critical | TC13 | Remove dependent validation | Functional | Y | - | - | -